## Gaz
USER ACCEPTANCE TEST
APPLICATION INFORMATION | [5 empty] | SYSTEM ACCESS LEVEL |  |  | UAT STATUS
ID | Description | Category | Related Functionality/Capability | Severity | Screen session # | Vendor | MDS Operation | Client/Management | Status (Pass/Fail) | Name of the Tester | Documented By | NOTE
MASTER DATA
1 | Venue Type / Destination Venue | Venue type field is mapped to stadiums and non stadiums ,final Destination Venue field is mapped in the "Final Destination Venue "This field is available at the "Make a booking" screen. | Make a booking > Scheduling Information | High | 1-Destination Venue | Available | Available | Not Available | Fail | Gzanfer Raqib | Shamir | - "Venue Type" should be replaced with "Site" - All should be listed; preferably with Stadiums at the top followed by a space and then all other venues
2 | Vehicle Types | Vehicle Types is mapped in the "Delivery Vehicle Type" data field . This dropdown field should display all destination venues. This field is available at the "Make a booking" screen. On select, a single item from the list should be selected. | Make a booking > Scheduling Information | Low | 2-Vehicle Type | Available | Available | Not Available | Fail | Gzanfer Raqib | Shamir | - More detailed list needs to be provided
3 | Functional Area(FA) | Functional Area is mapped with the drop down field " Functional Area". All functional areas from master data should be available in this dropdown. This field is available in "Make a booking" Screen.On select, a single item from the list should be selected. | Make a booking>Booking Details | Low | 3-Functional Area | Available | Available | Not Available | Fail | Gzanfer Raqib | Shamir | - "Functional Area" drop-down should list all Q22 and SC FAs - In some cases, there'll be no Functional Area link (e.g. Teams, Broadcasters, Commercial Affiliates)
4 | RSP | RSP is a assigned at system level based on the Delivery stadium and Non-Stadium location while confirmed booking. | Make a booking>Booking Details | High | 4-RSP Arrival Time | Available | Available | Not Available | Fail | Gzanfer Raqib | Shamir | - Needs to be shown to the User once they've selected their Site
5 | Cargo Description | Cargo Description is mapped with the dropdown field "Delivery Cargo Description" and "PickUp Cargo Description" in "Make a booking Screen. These feilds will be visible only if Delivery" Item is selected in "Delivery,Collecting or both" dropdown field. | Make a booking>Booking Details | Low | 5-Cargo Description | Available | Available | Not Available | Pass | Gzanfer Raqib | Shamir
6 | Purpose of Visit | Purpose if visit is mapped with the dropdown field " Delivering, collecting or both?" in "make by booking" screen". On select, a single item from the list should be selected. | Make a booking>Booking Details | Low | 6-Purpose of Visit | Available | Available | Not Available | Pass | Gzanfer Raqib | Shamir
TRANSACTIONAL DATA
7 | Launch URL on Google Chrome/Mozilla Firefox/MS Edge web browser | Type URL on google chrome and press enter.This will open SignUp/login page in MDS-Voyage Control portal | <https://gwctest.voyagecontrol.com/> | High | 7-URL Launch | Available | Available | Available | Pass | Gzanfer Raqib | Shamir
8 | SignUp New User | When User open the new signup form and fill up all the required fields and click "Register", the user should be redirected to login screen without any error.. | Login Screen>Signup | High | 8-SignUp New User | Available | Available | Available | Pass | Gzanfer Raqib | Shamir
9 | Email Notification for Email Verification | User will receive an email to the registered email address with a link. On click, the link should redirect to a new screen where user should enter registered company name. After submitting the verification is completed successfully. | Email>link | High | 9-Email Notification for email verification | Available | Available | Available | Pass | Gzanfer Raqib | Shamir | clean up wording in verification email: "Welcome to Voyage Control with Master Delivery Schedule! You recently created an account on Master Delivery Schedule of the Voyage Control."
10 | Email Notification for Registration Confirmation | In this email a "Get Started" link available. On click this link should redirect the user to home screen of MDS system | Email>Get Started | Low | 10-Email Notification for registration Confirmation | Available | Available | Available | Pass | Gzanfer Raqib | Shamir | Welcome to the Voyage Control booking system for Master Delivery Schedule. This is a free service that has been designed to reduce congestion and manage traffic flows for vehicles delivering and picking up from Master Delivery Schedule. The system allows you to book your vehicle into a time slot at the site, enabling you to come directly to site, reducing any delays. Simply make a booking to get your vehicle pass.
11 | Approve New User | MDS Admin removed the "Default" role and assigned "Approved User" role for the user. Once this is given a notification email should sent to the user and user should able to view "make a booking" and "list all booking" option on the left pane on screen. | Hub Management>User Role Permissions | Medium | 11-Email Notification for Approved User | Available | Available | Available | Pass | Gzanfer Raqib | Shamir
12 | Email Notification for User Approval | User should receive an email from MDS system once MDS admin approve the user | Email | Medium |  | Available | Available | Available | Pass | Gzanfer Raqib | Shamir
13 | Make a Booking | User fill in all the required information and the system should submit the new booking request successfully. | Make a booking | Low | 13.1-Make a Booking 13.2-Make a Booking | Available | Available | Not Available | Fail | Gzanfer Raqib | Shamir | - "Venue Type" should be replaced with "Site" - All should be listed; preferably with Stadiums at the top followed by a space and then all other venues - Delivery type should be listed first before Functional Area - - this should be a mandatory field - "Select time at RSP" wording should be changed as not all venues require to be delivering via an RSP. - "Functional Area" drop-down should list all Q22 and SC FAs - Guidance to be given that Driver and Vehicles details are mandatory, but editable before delivery. - More options need to be made avaialble for Delivery Vehicle type - Not all sites require Accreditation. The Accreditation answer needs to link to the site(s) that's being delivered to. - Delivery note attachment is currently optional
14 | Booking Confirmation | A booking confirmation screen will be displayed with Booking reference number and a button to open booking details and Make another booking | Make a booking | Low | 14-Booking Confirmation Screen | Available | Available | Not Available | Pass | Gzanfer Raqib | Shamir
15 | See Booking Details | On click "See booking details" button, a popup should open whern all booking details can be verified. | Make a booking | High | 15-See Booking Details Before approval | Available | Available | Not Available | Fail | Gzanfer Raqib | Shamir | If applicable, this should show the allocated RSP
16 | Email Notification for Booking Pending Approval | An email notification with status as "Booking Pending" is received in registered email of user after the booking successfully created | Email | Low | 16-Email Notification for booking approval Pending | Available | Available | Not Available | Pass | Gzanfer Raqib | Shamir | Wording needs to be fixed in email.
17 | List all bookings | User can view all the bookings. Onclick any booking will open as popup with booking details | List of booking | Medium | 17-List of bookings created by User | Available | Available | Not Available | Pass | Gzanfer Raqib | Shamir | Default dates should be at least a one month look ahead
18 | Download bookings | On click download button, user can download the selected booking directly. Or else an email will be send if all bookinng need to be downloaded. The downloaded file will be in excel format. | List of booking>Download | High | 18-Download bookings | Available | Available | Not Available | Pass | Gzanfer Raqib | Shamir
19 | Approve booking | MDS admin verify and approve the booking. The successful booking will send a email notification and change the status from "for approval" to " | List of Booking>Approve | High | 19-Approve Booking | Not Available | Available | Not Available | Pass | Gzanfer Raqib | Shamir | Need to test from Admin side
20 | Email notification to vendor after booking confirmed | An email notificaition should be received by vendor when MDS Approve the booking. The email should include a QR code and all basic information/\ | Email | Low | 20-Email notification for booking confirmation | Available | Not Available | Not Available | Fail | Gzanfer Raqib | Shamir | Email received, however wording needs imporving, including the need to include RSP location (if required).
21 | Email notification after booking confirmation -MDS Admin | An email notification should be received by MDS Admin members when any one of MDS Admin approve the booking | Email | Low | 21-Email notification for booking Confirmation | Not Available | Available | Not Available | Fail | Gzanfer Raqib | Shamir | What's the difference between this and ID:20?
22 | Email notification for vehicle check in | At RSP, When status has been updated to check in, an email notification will be received by Vendor with status "Delivery arrived" | email | Low | 22-Email Notification for vehicle check in | Available | Available | Not Available | Fail - Not tested | Gzanfer Raqib | Shamir
23 | Download Pass | On click pass from the popup, a pdf will be downloaded with QR Code and all booking details. | List of booking>Pass | High | 23-Pass-GWC10116310 | Available | Available | Not Available | Fail | Gzanfer Raqib | Shamir | - Remove reference to "Exhbitor" - Should "Loading Dock" read "RSP"..? - Remove "Stand Number" - update "2ndDelCargoDec" etc. - - reminder that for most people, English will not be their first language - Be clear that the Logistics support is for 1 hour - "Accredited Driver" should appear next to driver details
24 | Email notification for vehicle Check Out | At RSP, When status has been updated to checkout, an email notification will be received by Vendor with status "Checked Out" | Email | Low | 24-Email Notification for vehicle Check Out | Available | Available | Not Available | Fail - Not tested | Gzanfer Raqib | Shamir | -
25 | Password Reset | Click "Forget password" on login screen and user should provide the registered email address.A popup message has to be displayed | Login>Forgot Password | Medium | 25-Password Reset | Available | Available | Available | Pass | Gzanfer Raqib | Shamir
26 | Email Notification for Password Reset | The email should have a link wherein user onclick should redirect to new screen to change password. On press "Change by Password" button, it should successfully change the password. | Email>link | Medium | 26-Email Notification for password Reset | Available | Available | Available | Fail | Gzanfer Raqib | Shamir | Email not received and user is stuck without permissions. User would need to have the login link handy to try their new password.
27 | Terms and condition | On click "Terms and Condition" , the URL redirect to the webpage which contains Venue delivery guide . The page should open an new tab in web browser. | SignUp Screen | Medium | 27-SignUp Terms and Condition | Available | Available | Available | Fail | Gzanfer Raqib | Shamir | Terms and Conditions not found on Sign Up / Login page
28 | Change login Email | Enter new email in the "Change Login Email" section and press the button . This will successfully send an email notification to new address. | Settings>Account | Medium | 28-Change Login Email | Available | Available | Available | Pass | Gzanfer Raqib | Shamir
29 | Decline Booking | MDS Adminc an decline the booking. After pressing the button "decline" , the status of the booking will be updated to "Declined" | List of booking>Decline | High | 29-Decline Booking by MDS Admin | Available | Available | Not Available | Pass | Gzanfer Raqib | Shamir | Need to test from Admin side
30 | Email Notification for booking Declined | An email notification will be received to the vendor when the booking has been declined by MDS Admin with subject "Booking Declined" | Email | low | 30-Email notification for booking declined | Available | Available | Not Available | Pass | Gzanfer Raqib | Shamir
31 | Cancel Booking | MDS Admin and Normal Users can cancel the booking. ON click "Cancel" button on the screen, a new window will open. User provide the requireed details. This should succeesfully cancel the booking.and status should be updated as well. | List of booking>Cancel | High | 31-Cancel booking by MDS Admin | Available | Available | Not Available | Pass | Gzanfer Raqib | Shamir
32 | Email notification of booking cancelled | An email notification will be received to the vendor when the booking has been cancellled by MDS Admin with subject "Booking Cancelled" | Email | Low | 32-Email Notification for booking cancellation | Available | Available | Not Available | Pass | Gzanfer Raqib | Shamir
33 | Booking Time limit | Make a booking will not be allowed for vendor if the selected time slot is within 48 hours from the booking time. | Make a booking | High |  | Not Available | Available | Not Available | Pass | Gzanfer Raqib | Shamir
VIEWS
34 | Check all views are working | In column configuration,change the view type from the list. The list should refresh with required columns. Try all views and check all the views are working properly. | List of Booking | Low | 33-List Views | Available | Available | Not Available | Pass | Gzanfer Raqib | Shamir
REPORTS AND ANALYTICS
35 | Reports | This screen is available only for users with admin roles. Based on various filters, users can generate the Booking reports sucessfully. This report also can be downloaded in excel format and save in the system and open it without error. | Analytics | Low | 34-Reports | Not Available | Available | Available | Fail - Not tested | Gzanfer Raqib | Shamir

## Alaa
USER ACCEPTANCE TEST
APPLICATION INFORMATION | [5 empty] | SYSTEM ACCESS LEVEL |  |  | UAT STATUS
ID | Description | Category | Related Functionality/Capability | Severity | Screen session # | Vendor | MDS Operation | Client/Management | Status (Pass/Fail) | Name of the Tester | Documented By | NOTE
MASTER DATA
1 | Venue Type / Destination Venue | Venue type field is mapped to stadiums and non stadiums ,final Destination Venue field is mapped in the "Final Destination Venue "This field is available at the "Make a booking" screen. | Make a booking > Scheduling Information | High | 1-Destination Venue | Available | Available | Not Available |  |  | Shamir
2 | Vehicle Types | Vehicle Types is mapped in the "Delivery Vehicle Type" data field . This dropdown field should display all destination venues. This field is available at the "Make a booking" screen. On select, a single item from the list should be selected. | Make a booking > Scheduling Information | Low | 2-Vehicle Type | Available | Available | Not Available |  |  | Shamir
3 | Functional Area(FA) | Functional Area is mapped with the drop down field " Functional Area". All functional areas from master data should be available in this dropdown. This field is available in "Make a booking" Screen.On select, a single item from the list should be selected. | Make a booking>Booking Details | Low | 3-Functional Area | Available | Available | Not Available |  |  | Shamir
4 | RSP | RSP is a assigned at system level based on the Delivery stadium and Non-Stadium location while confirmed booking. | Make a booking>Booking Details | High | 4-RSP Arrival Time | Available | Available | Not Available |  |  | Shamir
5 | Cargo Description | Cargo Description is mapped with the dropdown field "Delivery Cargo Description" and "PickUp Cargo Description" in "Make a booking Screen. These feilds will be visible only if Delivery" Item is selected in "Delivery,Collecting or both" dropdown field. | Make a booking>Booking Details | Low | 5-Cargo Description | Available | Available | Not Available |  |  | Shamir
6 | Purpose of Visit | Purpose if visit is mapped with the dropdown field " Delivering, collecting or both?" in "make by booking" screen". On select, a single item from the list should be selected. | Make a booking>Booking Details | Low | 6-Purpose of Visit | Available | Available | Not Available |  |  | Shamir
TRANSACTIONAL DATA
7 | Launch URL on Google Chrome/Mozilla Firefox/MS Edge web browser | Type URL on google chrome and press enter.This will open SignUp/login page in MDS-Voyage Control portal | <https://gwctest.voyagecontrol.com/> | High | 7-URL Launch | Available | Available | Available | pass | Alaa | Shamir
8 | SignUp New User | When User open the new signup form and fill up all the required fields and click "Register", the user should be redirected to login screen without any error.. | Login Screen>Signup | High | 8-SignUp New User | Available | Available | Available | Pass | Alaa | Shamir | The Postcode is mandatory field, and I don’t have on in qatar, I have inserted 00000 instead
9 | Email Notification for Email Verification | User will receive an email to the registered email address with a link. On click, the link should redirect to a new screen where user should enter registered company name. After submitting the verification is completed successfully. | Email>link | High | 9-Email Notification for email verification | Available | Available | Available | Pass | Alaa | Shamir | I got the email instantanously, Verified and fill in the company name
10 | Email Notification for Registration Confirmation | In this email a "Get Started" link available. On click this link should redirect the user to home screen of MDS system | Email>Get Started | Low | 10-Email Notification for registration Confirmation | Available | Available | Available | Pass | Alaa | Shamir | I got the email instantanously
11 | Approve New User | MDS Admin removed the "Default" role and assigned "Approved User" role for the user. Once this is given a notification email should sent to the user and user should able to view "make a booking" and "list all booking" option on the left pane on screen. | Hub Management>User Role Permissions | Medium | 11-Email Notification for Approved User | Available | Available | Available | pass | Alaa | Shamir | The List of bookings was showing at after the login screen, after approvedstatus I have make a booking available
12 | Email Notification for User Approval | User should receive an email from MDS system once MDS admin approve the user | Email | Medium |  | Available | Available | Available | Fail | Alaa | Shamir | I havent receive any email of status change
13 | Make a Booking | User fill in all the required information and the system should submit the new booking request successfully. | Make a booking | Low | 13.1-Make a Booking 13.2-Make a Booking | Available | Available | Not Available | Pass | Alaa | Shamir | System requires an RSP booking for non-stadium sites as well as stadiums
14 | Booking Confirmation | A booking confirmation screen will be displayed with Booking reference number and a button to open booking details and Make another booking | Make a booking | Low | 14-Booking Confirmation Screen | Available | Available | Not Available | pass | Alaa | Shamir | received two emails immediately, one for booking pending approval, and one for logistical support | Still RSP is identified as Qatar Free Zone
15 | See Booking Details | On click "See booking details" button, a popup should open whern all booking details can be verified. | Make a booking | High | 15-See Booking Details Before approval | Available | Available | Not Available | pass | Alaa | Shamir
16 | Email Notification for Booking Pending Approval | An email notification with status as "Booking Pending" is received in registered email of user after the booking successfully created | Email | Low | 16-Email Notification for booking approval Pending | Available | Available | Not Available | pass | Alaa | Shamir
17 | List all bookings | User can view all the bookings. Onclick any booking will open as popup with booking details | List of booking | Medium | 17-List of bookings created by User | Available | Available | Not Available | Pass | Alaa | Shamir
18 | Download bookings | On click download button, user can download the selected booking directly. Or else an email will be send if all bookinng need to be downloaded. The downloaded file will be in excel format. | List of booking>Download | High | 18-Download bookings | Available | Available | Not Available | pass | Alaa | Shamir
19 | Approve booking | MDS admin verify and approve the booking. The successful booking will send a email notification and change the status from "for approval" to " | List of Booking>Approve | High | 19-Approve Booking | Not Available | Available | Not Available | pass | Alaa | Shamir
20 | Email notification to vendor after booking confirmed | An email notificaition should be received by vendor when MDS Approve the booking. The email should include a QR code and all basic information/\ | Email | Low | 20-Email notification for booking confirmation | Available | Not Available | Not Available | pass | Alaa | Shamir
21 | Email notification after booking confirmation -MDS Admin | An email notification should be received by MDS Admin members when any one of MDS Admin approve the booking | Email | Low | 21-Email notification for booking Confirmation | Not Available | Available | Not Available | pass | Alaa | Shamir
22 | Email notification for vehicle check in | At RSP, When status has been updated to check in, an email notification will be received by Vendor with status "Delivery arrived" | email | Low | 22-Email Notification for vehicle check in | Available | Available | Not Available | ? |  | Shamir
23 | Download Pass | On click pass from the popup, a pdf will be downloaded with QR Code and all booking details. | List of booking>Pass | High | 23-Pass-GWC10116310 | Available | Available | Not Available | pass | Alaa | Shamir
24 | Email notification for vehicle Check Out | At RSP, When status has been updated to checkout, an email notification will be received by Vendor with status "Checked Out" | Email | Low | 24-Email Notification for vehicle Check Out | Available | Available | Not Available | ? |  | Shamir
25 | Password Reset | Click "Forget password" on login screen and user should provide the registered email address.A popup message has to be displayed | Login>Forgot Password | Medium | 25-Password Reset | Available | Available | Available | pass | Alaa | Shamir
26 | Email Notification for Password Reset | The email should have a link wherein user onclick should redirect to new screen to change password. On press "Change by Password" button, it should successfully change the password. | Email>link | Medium | 26-Email Notification for password Reset | Available | Available | Available | pass | Alaa | Shamir
27 | Terms and condition | On click "Terms and Condition" , the URL redirect to the webpage which contains Venue delivery guide . The page should open an new tab in web browser. | SignUp Screen | Medium | 27-SignUp Terms and Condition | Available | Available | Available | Fial | Alaa | Shamir | Link directs to Voyage Control Website
28 | Change login Email | Enter new email in the "Change Login Email" section and press the button . This will successfully send an email notification to new address. | Settings>Account | Medium | 28-Change Login Email | Available | Available | Available |  |  | Shamir
29 | Decline Booking | MDS Adminc an decline the booking. After pressing the button "decline" , the status of the booking will be updated to "Declined" | List of booking>Decline | High | 29-Decline Booking by MDS Admin | Available | Available | Not Available |  |  | Shamir
30 | Email Notification for booking Declined | An email notification will be received to the vendor when the booking has been declined by MDS Admin with subject "Booking Declined" | Email | low | 30-Email notification for booking declined | Available | Available | Not Available |  |  | Shamir
31 | Cancel Booking | MDS Admin and Normal Users can cancel the booking. ON click "Cancel" button on the screen, a new window will open. User provide the requireed details. This should succeesfully cancel the booking.and status should be updated as well. | List of booking>Cancel | High | 31-Cancel booking by MDS Admin | Available | Available | Not Available | pass | Alaa | Shamir
32 | Email notification of booking cancelled | An email notification will be received to the vendor when the booking has been cancellled by MDS Admin with subject "Booking Cancelled" | Email | Low | 32-Email Notification for booking cancellation | Available | Available | Not Available | pass | Alaa | Shamir
33 | Booking Time limit | Make a booking will not be allowed for vendor if the selected time slot is within 48 hours from the booking time. | Make a booking | High |  | Not Available | Available | Not Available |  |  | Shamir
VIEWS
34 | Check all views are working | In column configuration,change the view type from the list. The list should refresh with required columns. Try all views and check all the views are working properly. | List of Booking | Low | 33-List Views | Available | Available | Not Available | pass | Alaa | Shamir
REPORTS AND ANALYTICS
35 | Reports | This screen is available only for users with admin roles. Based on various filters, users can generate the Booking reports sucessfully. This report also can be downloaded in excel format and save in the system and open it without error. | Analytics | Low | 34-Reports | Not Available | Available | Available | pass | Alaa | Shamir

## Shadi
USER ACCEPTANCE TEST
APPLICATION INFORMATION | [5 empty] | SYSTEM ACCESS LEVEL |  |  | UAT STATUS
ID | Description | Category | Related Functionality/Capability | Severity | Screen session # | Vendor | MDS Operation | Client/Management | Status (Pass/Fail) | Name of the Tester | Documented By | NOTE
MASTER DATA
1 | Venue Type / Destination Venue | Venue type field is mapped to stadiums and non stadiums ,final Destination Venue field is mapped in the "Final Destination Venue "This field is available at the "Make a booking" screen. | Make a booking > Scheduling Information | High | 1-Destination Venue | Available | Available | Not Available | Passed | Shadi Safa | Shamir
2 | Vehicle Types | Vehicle Types is mapped in the "Delivery Vehicle Type" data field . This dropdown field should display all destination venues. This field is available at the "Make a booking" screen. On select, a single item from the list should be selected. | Make a booking > Scheduling Information | Low | 2-Vehicle Type | Available | Available | Not Available | Passed | Shadi Safa | Shamir
3 | Functional Area(FA) | Functional Area is mapped with the drop down field " Functional Area". All functional areas from master data should be available in this dropdown. This field is available in "Make a booking" Screen.On select, a single item from the list should be selected. | Make a booking>Booking Details | Low | 3-Functional Area | Available | Available | Not Available | Passed | Shadi Safa | Shamir
4 | RSP | RSP is a assigned at system level based on the Delivery stadium and Non-Stadium location while confirmed booking. | Make a booking>Booking Details | High | 4-RSP Arrival Time | Available | Available | Not Available | Passed | Shadi Safa | Shamir
5 | Cargo Description | Cargo Description is mapped with the dropdown field "Delivery Cargo Description" and "PickUp Cargo Description" in "Make a booking Screen. These feilds will be visible only if Delivery" Item is selected in "Delivery,Collecting or both" dropdown field. | Make a booking>Booking Details | Low | 5-Cargo Description | Available | Available | Not Available | Passed | Shadi Safa | Shamir
6 | Purpose of Visit | Purpose if visit is mapped with the dropdown field " Delivering, collecting or both?" in "make by booking" screen". On select, a single item from the list should be selected. | Make a booking>Booking Details | Low | 6-Purpose of Visit | Available | Available | Not Available |  | Shadi Safa | Shamir
TRANSACTIONAL DATA
7 | Launch URL on Google Chrome/Mozilla Firefox/MS Edge web browser | Type URL on google chrome and press enter.This will open SignUp/login page in MDS-Voyage Control portal | <https://gwctest.voyagecontrol.com/> | High | 7-URL Launch | Available | Available | Available | Passed | Shadi Safa | Shamir
8 | SignUp New User | When User open the new signup form and fill up all the required fields and click "Register", the user should be redirected to login screen without any error.. | Login Screen>Signup | High | 8-SignUp New User | Available | Available | Available | Passed | Shadi Safa | Shamir
9 | Email Notification for Email Verification | User will receive an email to the registered email address with a link. On click, the link should redirect to a new screen where user should enter registered company name. After submitting the verification is completed successfully. | Email>link | High | 9-Email Notification for email verification | Available | Available | Available | Passed | Shadi Safa | Shamir
10 | Email Notification for Registration Confirmation | In this email a "Get Started" link available. On click this link should redirect the user to home screen of MDS system | Email>Get Started | Low | 10-Email Notification for registration Confirmation | Available | Available | Available | Passed | Shadi Safa | Shamir
11 | Approve New User | MDS Admin removed the "Default" role and assigned "Approved User" role for the user. Once this is given a notification email should sent to the user and user should able to view "make a booking" and "list all booking" option on the left pane on screen. | Hub Management>User Role Permissions | Medium | 11-Email Notification for Approved User | Available | Available | Available | Passed | Shadi Safa | Shamir
12 | Email Notification for User Approval | User should receive an email from MDS system once MDS admin approve the user | Email | Medium |  | Available | Available | Available | Passed | Shadi Safa | Shamir
13 | Make a Booking | User fill in all the required information and the system should submit the new booking request successfully. | Make a booking | Low | 13.1-Make a Booking 13.2-Make a Booking | Available | Available | Not Available | Passed | Shadi Safa | Shamir | Point of Origin displays a popup asking for Postal code while it could be anything
14 | Booking Confirmation | A booking confirmation screen will be displayed with Booking reference number and a button to open booking details and Make another booking | Make a booking | Low | 14-Booking Confirmation Screen | Available | Available | Not Available | Passed | Shadi Safa | Shamir
15 | See Booking Details | On click "See booking details" button, a popup should open whern all booking details can be verified. | Make a booking | High | 15-See Booking Details Before approval | Available | Available | Not Available | Passed | Shadi Safa | Shamir | 1- In List of Bookings, in Second View Report, we can move the field headers but the Columns will stay the same. It gets back to normal after refresh. My suggestion is that either remove this functionality or work on moving the columns as well. 2- When you select a booking, can it be colored with the same status or have a small box with the same color.
16 | Email Notification for Booking Pending Approval | An email notification with status as "Booking Pending" is received in registered email of user after the booking successfully created | Email | Low | 16-Email Notification for booking approval Pending | Available | Available | Not Available | Passed | Shadi Safa | Shamir
17 | List all bookings | User can view all the bookings. Onclick any booking will open as popup with booking details | List of booking | Medium | 17-List of bookings created by User | Available | Available | Not Available | Passed | Shadi Safa | Shamir
18 | Download bookings | On click download button, user can download the selected booking directly. Or else an email will be send if all bookinng need to be downloaded. The downloaded file will be in excel format. | List of booking>Download | High | 18-Download bookings | Available | Available | Not Available | Passed | Shadi Safa | Shamir
19 | Approve booking | MDS admin verify and approve the booking. The successful booking will send a email notification and change the status from "for approval" to " | List of Booking>Approve | High | 19-Approve Booking | Not Available | Available | Not Available | Passed | Shadi Safa | Shamir
20 | Email notification to vendor after booking confirmed | An email notificaition should be received by vendor when MDS Approve the booking. The email should include a QR code and all basic information/\ | Email | Low | 20-Email notification for booking confirmation | Available | Not Available | Not Available | Passed | Shadi Safa | Shamir
21 | Email notification after booking confirmation -MDS Admin | An email notification should be received by MDS Admin members when any one of MDS Admin approve the booking | Email | Low | 21-Email notification for booking Confirmation | Not Available | Available | Not Available | Passed | Shadi Safa | Shamir
22 | Email notification for vehicle check in | At RSP, When status has been updated to check in, an email notification will be received by Vendor with status "Delivery arrived" | email | Low | 22-Email Notification for vehicle check in | Available | Available | Not Available | Passed | Shadi Safa | Shamir
23 | Download Pass | On click pass from the popup, a pdf will be downloaded with QR Code and all booking details. | List of booking>Pass | High | 23-Pass-GWC10116310 | Available | Available | Not Available | Passed | Shadi Safa | Shamir
24 | Email notification for vehicle Check Out | At RSP, When status has been updated to checkout, an email notification will be received by Vendor with status "Checked Out" | Email | Low | 24-Email Notification for vehicle Check Out | Available | Available | Not Available | Passed | Shadi Safa | Shamir
25 | Password Reset | Click "Forget password" on login screen and user should provide the registered email address.A popup message has to be displayed | Login>Forgot Password | Medium | 25-Password Reset | Available | Available | Available | Passed | Shadi Safa | Shamir
26 | Email Notification for Password Reset | The email should have a link wherein user onclick should redirect to new screen to change password. On press "Change by Password" button, it should successfully change the password. | Email>link | Medium | 26-Email Notification for password Reset | Available | Available | Available | Passed | Shadi Safa | Shamir
27 | Terms and condition | On click "Terms and Condition" , the URL redirect to the webpage which contains Venue delivery guide . The page should open an new tab in web browser. | SignUp Screen | Medium | 27-SignUp Terms and Condition | Available | Available | Available | Passed | Shadi Safa | Shamir
28 | Change login Email | Enter new email in the "Change Login Email" section and press the button . This will successfully send an email notification to new address. | Settings>Account | Medium | 28-Change Login Email | Available | Available | Available | Passed | Shadi Safa | Shamir
29 | Decline Booking | MDS Adminc an decline the booking. After pressing the button "decline" , the status of the booking will be updated to "Declined" | List of booking>Decline | High | 29-Decline Booking by MDS Admin | Available | Available | Not Available | Passed | Shadi Safa | Shamir
30 | Email Notification for booking Declined | An email notification will be received to the vendor when the booking has been declined by MDS Admin with subject "Booking Declined" | Email | low | 30-Email notification for booking declined | Available | Available | Not Available | Passed | Shadi Safa | Shamir
31 | Cancel Booking | MDS Admin and Normal Users can cancel the booking. ON click "Cancel" button on the screen, a new window will open. User provide the requireed details. This should succeesfully cancel the booking.and status should be updated as well. | List of booking>Cancel | High | 31-Cancel booking by MDS Admin | Available | Available | Not Available | Passed | Shadi Safa | Shamir
32 | Email notification of booking cancelled | An email notification will be received to the vendor when the booking has been cancellled by MDS Admin with subject "Booking Cancelled" | Email | Low | 32-Email Notification for booking cancellation | Available | Available | Not Available | Passed | Shadi Safa | Shamir
33 | Booking Time limit | Make a booking will not be allowed for vendor if the selected time slot is within 48 hours from the booking time. | Make a booking | High |  | Not Available | Available | Not Available | Passed | Shadi Safa | Shamir | It is better to display the 48 time restriction in the message
VIEWS
34 | Check all views are working | In column configuration,change the view type from the list. The list should refresh with required columns. Try all views and check all the views are working properly. | List of Booking | Low | 33-List Views | Available | Available | Not Available |  | Shadi Safa | Shamir
REPORTS AND ANALYTICS
35 | Reports | This screen is available only for users with admin roles. Based on various filters, users can generate the Booking reports sucessfully. This report also can be downloaded in excel format and save in the system and open it without error. | Analytics | Low | 34-Reports | Not Available | Available | Available |  | Shadi Safa | Shamir

## AZ
USER ACCEPTANCE TEST
APPLICATION INFORMATION | [5 empty] | SYSTEM ACCESS LEVEL |  |  | UAT STATUS
ID | Description | Category | Related Functionality/Capability | Severity | Screen session # | Vendor | MDS Operation | Client/Management | Status (Pass/Fail) | Name of the Tester | Documented By | NOTE
MASTER DATA
1 | Venue Type / Destination Venue | Venue type field is mapped to stadiums and non stadiums ,final Destination Venue field is mapped in the "Final Destination Venue "This field is available at the "Make a booking" screen. | Make a booking > Scheduling Information | High | 1-Destination Venue | Available | Available | Not Available | Fail | Andrey Zvyagintsev | Shamir | We have to check the logic of the system , how it manages masterdata "Venue Type/Destination Venue" and correct it properly
2 | Vehicle Types | Vehicle Types is mapped in the "Delivery Vehicle Type" data field . This dropdown field should display all destination venues. This field is available at the "Make a booking" screen. On select, a single item from the list should be selected. | Make a booking > Scheduling Information | Low | 2-Vehicle Type | Available | Available | Not Available | Fail | Andrey Zvyagintsev | Shamir | List should be corrected, SC to provide the list
3 | Functional Area(FA) | Functional Area is mapped with the drop down field " Functional Area". All functional areas from master data should be available in this dropdown. This field is available in "Make a booking" Screen.On select, a single item from the list should be selected. | Make a booking>Booking Details | Low | 3-Functional Area | Available | Available | Not Available | Fail | Andrey Zvyagintsev | Shamir | List should be corrected, SC&Q22 to provide the list. And try if it will fit the interface
4 | RSP | RSP is a assigned at system level based on the Delivery stadium and Non-Stadium location while confirmed booking. | Make a booking>Booking Details | High | 4-RSP Arrival Time | Available | Available | Not Available | Fail | Andrey Zvyagintsev | Shamir | We have to find a solution to make it more clear for the Applicant which RSP he should arrive. Moreover, in the list of Bookings RSP should be shifted left as much as possible
5 | Cargo Description | Cargo Description is mapped with the dropdown field "Delivery Cargo Description" and "PickUp Cargo Description" in "Make a booking Screen. These feilds will be visible only if Delivery" Item is selected in "Delivery,Collecting or both" dropdown field. | Make a booking>Booking Details | Low | 5-Cargo Description | Available | Available | Not Available | Pass | Andrey Zvyagintsev | Shamir | But needs small amendments, SC to provide the list
6 | Purpose of Visit | Purpose if visit is mapped with the dropdown field " Delivering, collecting or both?" in "make by booking" screen". On select, a single item from the list should be selected. | Make a booking>Booking Details | Low | 6-Purpose of Visit | Available | Available | Not Available | Pass | Andrey Zvyagintsev | Shamir | Would prefer to simplify
TRANSACTIONAL DATA
7 | Launch URL on Google Chrome/Mozilla Firefox/MS Edge web browser | Type URL on google chrome and press enter.This will open SignUp/login page in MDS-Voyage Control portal | <https://gwctest.voyagecontrol.com/> | High | 7-URL Launch | Available | Available | Available | Pass | Andrey Zvyagintsev | Shamir
8 | SignUp New User | When User open the new signup form and fill up all the required fields and click "Register", the user should be redirected to login screen without any error.. | Login Screen>Signup | High | 8-SignUp New User | Available | Available | Available | Pass | Andrey Zvyagintsev | Shamir | Need to check if it is possible to avoid postal code option
9 | Email Notification for Email Verification | User will receive an email to the registered email address with a link. On click, the link should redirect to a new screen where user should enter registered company name. After submitting the verification is completed successfully. | Email>link | High | 9-Email Notification for email verification | Available | Available | Available | Pass | Andrey Zvyagintsev | Shamir | Text to be confirmed (check marketing rights), VC support mail TBC
10 | Email Notification for Registration Confirmation | In this email a "Get Started" link available. On click this link should redirect the user to home screen of MDS system | Email>Get Started | Low | 10-Email Notification for registration Confirmation | Available | Available | Available | Pass | Andrey Zvyagintsev | Shamir | Text to be confirmed (check marketing rights), link about FAQ to be checked too
11 | Approve New User | MDS Admin removed the "Default" role and assigned "Approved User" role for the user. Once this is given a notification email should sent to the user and user should able to view "make a booking" and "list all booking" option on the left pane on screen. | Hub Management>User Role Permissions | Medium | 11-Email Notification for Approved User | Available | Available | Available | Pass | Andrey Zvyagintsev | Shamir
12 | Email Notification for User Approval | User should receive an email from MDS system once MDS admin approve the user | Email | Medium |  | Available | Available | Available | Pass | Andrey Zvyagintsev | Shamir
13 | Make a Booking | User fill in all the required information and the system should submit the new booking request successfully. | Make a booking | Low | 13.1-Make a Booking 13.2-Make a Booking | Available | Available | Not Available | Fail | Andrey Zvyagintsev | Shamir | We have to check the logic of the system , how it manages masterdata "Venue Type/Destination Venue" and correct it properly Select time at RSP - this field should be renamed according the logic of the system Vehicle - can we delete Make and Year? FA Contact - make it more clear what data needed Is it possible delete Accreditation option?
14 | Booking Confirmation | A booking confirmation screen will be displayed with Booking reference number and a button to open booking details and Make another booking | Make a booking | Low | 14-Booking Confirmation Screen | Available | Available | Not Available | Pass | Andrey Zvyagintsev | Shamir
15 | See Booking Details | On click "See booking details" button, a popup should open whern all booking details can be verified. | Make a booking | High | 15-See Booking Details Before approval | Available | Available | Not Available | Pass | Andrey Zvyagintsev | Shamir
16 | Email Notification for Booking Pending Approval | An email notification with status as "Booking Pending" is received in registered email of user after the booking successfully created | Email | Low | 16-Email Notification for booking approval Pending | Available | Available | Not Available | Pass | Andrey Zvyagintsev | Shamir | Text in the message to be corrected
17 | List all bookings | User can view all the bookings. Onclick any booking will open as popup with booking details | List of booking | Medium | 17-List of bookings created by User | Available | Available | Not Available | Pass | Andrey Zvyagintsev | Shamir | Interface shows short list, we have to extend the period (initial)
18 | Download bookings | On click download button, user can download the selected booking directly. Or else an email will be send if all bookinng need to be downloaded. The downloaded file will be in excel format. | List of booking>Download | High | 18-Download bookings | Available | Available | Not Available | Pass | Andrey Zvyagintsev | Shamir
19 | Approve booking | MDS admin verify and approve the booking. The successful booking will send a email notification and change the status from "for approval" to " | List of Booking>Approve | High | 19-Approve Booking | Not Available | Available | Not Available | Pass | Andrey Zvyagintsev | Shamir | Confirmation received
20 | Email notification to vendor after booking confirmed | An email notificaition should be received by vendor when MDS Approve the booking. The email should include a QR code and all basic information/\ | Email | Low | 20-Email notification for booking confirmation | Available | Not Available | Not Available | Pass | Andrey Zvyagintsev | Shamir | We have to change the text, include assigned RSP
21 | Email notification after booking confirmation -MDS Admin | An email notification should be received by MDS Admin members when any one of MDS Admin approve the booking | Email | Low | 21-Email notification for booking Confirmation | Not Available | Available | Not Available | Pass | Andrey Zvyagintsev | Shamir
22 | Email notification for vehicle check in | At RSP, When status has been updated to check in, an email notification will be received by Vendor with status "Delivery arrived" | email | Low | 22-Email Notification for vehicle check in | Available | Available | Not Available | Fail - Not tested | Andrey Zvyagintsev | Shamir | We have to test later
23 | Download Pass | On click pass from the popup, a pdf will be downloaded with QR Code and all booking details. | List of booking>Pass | High | 23-Pass-GWC10116310 | Available | Available | Not Available | Fail | Andrey Zvyagintsev | Shamir | Text to be edited, we have to understad which fields could be deleted
24 | Email notification for vehicle Check Out | At RSP, When status has been updated to checkout, an email notification will be received by Vendor with status "Checked Out" | Email | Low | 24-Email Notification for vehicle Check Out | Available | Available | Not Available | Fail - Not tested | Andrey Zvyagintsev | Shamir | We have to test later
25 | Password Reset | Click "Forget password" on login screen and user should provide the registered email address.A popup message has to be displayed | Login>Forgot Password | Medium | 25-Password Reset | Available | Available | Available | Pass | Andrey Zvyagintsev | Shamir
26 | Email Notification for Password Reset | The email should have a link wherein user onclick should redirect to new screen to change password. On press "Change by Password" button, it should successfully change the password. | Email>link | Medium | 26-Email Notification for password Reset | Available | Available | Available | Not tested | Andrey Zvyagintsev | Shamir
27 | Terms and condition | On click "Terms and Condition" , the URL redirect to the webpage which contains Venue delivery guide . The page should open an new tab in web browser. | SignUp Screen | Medium | 27-SignUp Terms and Condition | Available | Available | Available | Fail | Andrey Zvyagintsev | Shamir | We have to decide what information include here
28 | Change login Email | Enter new email in the "Change Login Email" section and press the button . This will successfully send an email notification to new address. | Settings>Account | Medium | 28-Change Login Email | Available | Available | Available | Pass | Andrey Zvyagintsev | Shamir
29 | Decline Booking | MDS Adminc an decline the booking. After pressing the button "decline" , the status of the booking will be updated to "Declined" | List of booking>Decline | High | 29-Decline Booking by MDS Admin | Available | Available | Not Available | Pass | Andrey Zvyagintsev | Shamir
30 | Email Notification for booking Declined | An email notification will be received to the vendor when the booking has been declined by MDS Admin with subject "Booking Declined" | Email | low | 30-Email notification for booking declined | Available | Available | Not Available | Pass | Andrey Zvyagintsev | Shamir
31 | Cancel Booking | MDS Admin and Normal Users can cancel the booking. ON click "Cancel" button on the screen, a new window will open. User provide the requireed details. This should succeesfully cancel the booking.and status should be updated as well. | List of booking>Cancel | High | 31-Cancel booking by MDS Admin | Available | Available | Not Available | Pass | Andrey Zvyagintsev | Shamir
32 | Email notification of booking cancelled | An email notification will be received to the vendor when the booking has been cancellled by MDS Admin with subject "Booking Cancelled" | Email | Low | 32-Email Notification for booking cancellation | Available | Available | Not Available | Pass | Andrey Zvyagintsev | Shamir
33 | Booking Time limit | Make a booking will not be allowed for vendor if the selected time slot is within 48 hours from the booking time. | Make a booking | High |  | Not Available | Available | Not Available | Pass | Andrey Zvyagintsev | Shamir
VIEWS
34 | Check all views are working | In column configuration,change the view type from the list. The list should refresh with required columns. Try all views and check all the views are working properly. | List of Booking | Low | 33-List Views | Available | Available | Not Available | Pass | Andrey Zvyagintsev | Shamir
REPORTS AND ANALYTICS
35 | Reports | This screen is available only for users with admin roles. Based on various filters, users can generate the Booking reports sucessfully. This report also can be downloaded in excel format and save in the system and open it without error. | Analytics | Low | 34-Reports | Not Available | Available | Available | Fail - Not tested | Andrey Zvyagintsev | Shamir

## Combined
USER ACCEPTANCE TEST
APPLICATION INFORMATION | [5 empty] | SYSTEM ACCESS LEVEL |  |  | UAT STATUS
ID | Description | Category | Related Functionality/Capability | Severity | Screen session # | Vendor | MDS Operation | Client/Management | Status (Pass/Fail) | Name of the Tester | Documented By | NOTE
MASTER DATA
1 | Venue Type / Destination Venue | Venue type field is mapped to stadiums and non stadiums ,final Destination Venue field is mapped in the "Final Destination Venue "This field is available at the "Make a booking" screen. | Make a booking > Scheduling Information | High | 1-Destination Venue | Available | Available | Not Available | Fail | Gzanfer Raqib | Shamir | GR: '- "Venue Type" should be replaced with "Site" - All should be listed; preferably with Stadiums at the top followed by a space and then all other venues AZ: We have to check the logic of the system , how it manages masterdata "Venue Type/Destination Venue" and correct it properly Check an opprotunity if we can change names of cells in Functional Area module
2 | Vehicle Types | Vehicle Types is mapped in the "Delivery Vehicle Type" data field . This dropdown field should display all destination venues. This field is available at the "Make a booking" screen. On select, a single item from the list should be selected. | Make a booking > Scheduling Information | Low | 2-Vehicle Type | Available | Available | Not Available | Fail | Gzanfer Raqib | Shamir | GR:'- More detailed list needs to be provided AZ: List should be corrected, SC to provide the list
3 | Functional Area(FA) | Functional Area is mapped with the drop down field " Functional Area". All functional areas from master data should be available in this dropdown. This field is available in "Make a booking" Screen.On select, a single item from the list should be selected. | Make a booking>Booking Details | Low | 3-Functional Area | Available | Available | Not Available | Fail | Gzanfer Raqib | Shamir | GR:'- "Functional Area" drop-down should list all Q22 and SC FAs - In some cases, there'll be no Functional Area link (e.g. Teams, Broadcasters, Commercial Affiliates) AZ: List should be corrected, SC&Q22 to provide the list. And try if it will fit the interface
4 | RSP | RSP is a assigned at system level based on the Delivery stadium and Non-Stadium location while confirmed booking. | Make a booking>Booking Details | High | 4-RSP Arrival Time | Available | Available | Not Available | Fail | Gzanfer Raqib | Shamir | GR:'- Needs to be shown to the User once they've selected their Site AZ:We have to find a solution to make it more clear for the Applicant which RSP he should arrive. Moreover, in the list of Bookings RSP should be shifted left as much as possible
5 | Cargo Description | Cargo Description is mapped with the dropdown field "Delivery Cargo Description" and "PickUp Cargo Description" in "Make a booking Screen. These feilds will be visible only if Delivery" Item is selected in "Delivery,Collecting or both" dropdown field. | Make a booking>Booking Details | Low | 5-Cargo Description | Available | Available | Not Available | Pass | Gzanfer Raqib | Shamir | AZ: But needs small amendments, SC to provide the list
6 | Purpose of Visit | Purpose if visit is mapped with the dropdown field " Delivering, collecting or both?" in "make by booking" screen". On select, a single item from the list should be selected. | Make a booking>Booking Details | Low | 6-Purpose of Visit | Available | Available | Not Available | Pass | Gzanfer Raqib | Shamir | AZ: Would prefer to simplify
TRANSACTIONAL DATA
7 | Launch URL on Google Chrome/Mozilla Firefox/MS Edge web browser | Type URL on google chrome and press enter.This will open SignUp/login page in MDS-Voyage Control portal | <https://gwctest.voyagecontrol.com/> | High | 7-URL Launch | Available | Available | Available | Pass | Gzanfer Raqib | Shamir
8 | SignUp New User | When User open the new signup form and fill up all the required fields and click "Register", the user should be redirected to login screen without any error.. | Login Screen>Signup | High | 8-SignUp New User | Available | Available | Available | Pass | Gzanfer Raqib | Shamir | AA: The Postcode is mandatory field, and I don’t have on in qatar, I have inserted 00000 instead AZ: Need to check if it is possible to avoid postal code option
9 | Email Notification for Email Verification | User will receive an email to the registered email address with a link. On click, the link should redirect to a new screen where user should enter registered company name. After submitting the verification is completed successfully. | Email>link | High | 9-Email Notification for email verification | Available | Available | Available | Pass | Gzanfer Raqib | Shamir | GR:clean up wording in verification email: "Welcome to Voyage Control with Master Delivery Schedule! You recently created an account on Master Delivery Schedule of the Voyage Control." AA: I got the email instantanously, Verified and fill in the company name AZ: Text to be confirmed (check marketing rights), VC support mail TBC
10 | Email Notification for Registration Confirmation | In this email a "Get Started" link available. On click this link should redirect the user to home screen of MDS system | Email>Get Started | Low | 10-Email Notification for registration Confirmation | Available | Available | Available | Pass | Gzanfer Raqib | Shamir | GR:Welcome to the Voyage Control booking system for Master Delivery Schedule. This is a free service that has been designed to reduce congestion and manage traffic flows for vehicles delivering and picking up from Master Delivery Schedule. The system allows you to book your vehicle into a time slot at the site, enabling you to come directly to site, reducing any delays. Simply make a booking to get your vehicle pass. AA:I got the email instantanously AZ: Text to be confirmed (check marketing rights), link about FAQ to be checked too
11 | Approve New User | MDS Admin removed the "Default" role and assigned "Approved User" role for the user. Once this is given a notification email should sent to the user and user should able to view "make a booking" and "list all booking" option on the left pane on screen. | Hub Management>User Role Permissions | Medium | 11-Email Notification for Approved User | Available | Available | Available | Pass | Gzanfer Raqib | Shamir | The List of bookings was showing at after the login screen, after approvedstatus I have make a booking available
12 | Email Notification for User Approval | User should receive an email from MDS system once MDS admin approve the user | Email | Medium |  | Available | Available | Available | Pass | Gzanfer Raqib | Shamir | I havent receive any email of status change
13 | Make a Booking | User fill in all the required information and the system should submit the new booking request successfully. | Make a booking | Low | 13.1-Make a Booking 13.2-Make a Booking | Available | Available | Not Available | Fail | Gzanfer Raqib | Shamir | GR:'- "Venue Type" should be replaced with "Site" - All should be listed; preferably with Stadiums at the top followed by a space and then all other venues - Delivery type should be listed first before Functional Area - - this should be a mandatory field - "Select time at RSP" wording should be changed as not all venues require to be delivering via an RSP. - "Functional Area" drop-down should list all Q22 and SC FAs - Guidance to be given that Driver and Vehicles details are mandatory, but editable before delivery. - More options need to be made avaialble for Delivery Vehicle type - Not all sites require Accreditation. The Accreditation answer needs to link to the site(s) that's being delivered to. - Delivery note attachment is currently optional AA: System requires an RSP booking for non-stadium sites as well as stadiums SS:Point of Origin displays a popup asking for Postal code while it could be anything AZ: We have to check the logic of the system , how it manages masterdata "Venue Type/Destination Venue" and correct it properly Select time at RSP - this field should be renamed according the logic of the system (we will add info accordingly about time of arrival) Vehicle - can we delete Make and Year? FA Contact - make it more clear what data needed Is it possible delete Accreditation option? Is it possible to block Point of Journey cell (I am not sure we need it, it adds more misunderstanding for the Supplier Could we change the name of "Delivery Note" option to be more clear for the supplier: Delivery Note (or Invoice/Packing List/List of Cargo)? When you try to pick up driver/vehicle from the drop-down list, it is hard to pick it up from the first time (not very important, indeed)
14 | Booking Confirmation | A booking confirmation screen will be displayed with Booking reference number and a button to open booking details and Make another booking | Make a booking | Low | 14-Booking Confirmation Screen | Available | Available | Not Available | Pass | Gzanfer Raqib | Shamir | AA: received two emails immediately, one for booking pending approval, and one for logistical support AZ: As soon as we understand if the mail about Log support could be sent to LCC address , we have to change the text in the confirmationfor the Supplier: "• “A request for MHE and labour services with your MDS booking is not guaranteed. If you do not have MHE and labour support services confirmed with the Logistics Coordination Centre (LCC) ahead of your MDS delivery/collection, please contact the LCC or ensure that you have arranged these services yourself.”
15 | See Booking Details | On click "See booking details" button, a popup should open whern all booking details can be verified. | Make a booking | High | 15-See Booking Details Before approval | Available | Available | Not Available | Fail | Gzanfer Raqib | Shamir | GR:If applicable, this should show the allocated RSP SS: 1- In List of Bookings, in Second View Report, we can move the field headers but the Columns will stay the same. It gets back to normal after refresh. My suggestion is that either remove this functionality or work on moving the columns as well. 2- When you select a booking, can it be colored with the same status or have a small box with the same color. AZ: We have to block an "Edit" opportunity for confirmed booking. To block the button. The system does not make changes, but the Supplier thinks it does. It will be misunderstanding Another fact: After cancellation of Booking when you try to use option "Duplicate" an error appears" Server Error"
16 | Email Notification for Booking Pending Approval | An email notification with status as "Booking Pending" is received in registered email of user after the booking successfully created | Email | Low | 16-Email Notification for booking approval Pending | Available | Available | Not Available | Pass | Gzanfer Raqib | Shamir | GR:Wording needs to be fixed in email. AZ: Text in the message to be corrected
17 | List all bookings | User can view all the bookings. Onclick any booking will open as popup with booking details | List of booking | Medium | 17-List of bookings created by User | Available | Available | Not Available | Pass | Gzanfer Raqib | Shamir | GR:Default dates should be at least a one month look ahead AZ: Interface shows short list, we have to extend the period (initial) When you try to change columns in Second View report and create new configuration , it is "Server error" (not so important, but still an error) "User Type" in the list of bookings can't be clear for me (it is venue name), we have to understand the logic of the system how it forms this report/list
18 | Download bookings | On click download button, user can download the selected booking directly. Or else an email will be send if all bookinng need to be downloaded. The downloaded file will be in excel format. | List of booking>Download | High | 18-Download bookings | Available | Available | Not Available | Pass | Gzanfer Raqib | Shamir
19 | Approve booking | MDS admin verify and approve the booking. The successful booking will send a email notification and change the status from "for approval" to " | List of Booking>Approve | High | 19-Approve Booking | Not Available | Available | Not Available | Pass | Gzanfer Raqib | Shamir | GR:Need to test from Admin side AZ: Confirmation received
20 | Email notification to vendor after booking confirmed | An email notificaition should be received by vendor when MDS Approve the booking. The email should include a QR code and all basic information/\ | Email | Low | 20-Email notification for booking confirmation | Available | Not Available | Not Available | Fail | Gzanfer Raqib | Shamir | GR:Email received, however wording needs imporving, including the need to include RSP location (if required). AZ: We have to change the text, include assigned RSP
21 | Email notification after booking confirmation -MDS Admin | An email notification should be received by MDS Admin members when any one of MDS Admin approve the booking | Email | Low | 21-Email notification for booking Confirmation | Not Available | Available | Not Available | Fail | Gzanfer Raqib | Shamir | GR:What's the difference between this and ID:20?
22 | Email notification for vehicle check in | At RSP, When status has been updated to check in, an email notification will be received by Vendor with status "Delivery arrived" | email | Low | 22-Email Notification for vehicle check in | Available | Available | Not Available | Fail - Not tested | Gzanfer Raqib | Shamir | AZ: We have to test later
23 | Download Pass | On click pass from the popup, a pdf will be downloaded with QR Code and all booking details. | List of booking>Pass | High | 23-Pass-GWC10116310 | Available | Available | Not Available | Fail | Gzanfer Raqib | Shamir | GR:'- Remove reference to "Exhbitor" - Should "Loading Dock" read "RSP"..? - Remove "Stand Number" - update "2ndDelCargoDec" etc. - - reminder that for most people, English will not be their first language - Be clear that the Logistics support is for 1 hour - "Accredited Driver" should appear next to driver details AZ: Text to be edited, we have to understad which fields could be deleted
24 | Email notification for vehicle Check Out | At RSP, When status has been updated to checkout, an email notification will be received by Vendor with status "Checked Out" | Email | Low | 24-Email Notification for vehicle Check Out | Available | Available | Not Available | Fail - Not tested | Gzanfer Raqib | Shamir | AZ: We have to test later
25 | Password Reset | Click "Forget password" on login screen and user should provide the registered email address.A popup message has to be displayed | Login>Forgot Password | Medium | 25-Password Reset | Available | Available | Available | Pass | Gzanfer Raqib | Shamir
26 | Email Notification for Password Reset | The email should have a link wherein user onclick should redirect to new screen to change password. On press "Change by Password" button, it should successfully change the password. | Email>link | Medium | 26-Email Notification for password Reset | Available | Available | Available | Fail | Gzanfer Raqib | Shamir | GR:Email not received and user is stuck without permissions. User would need to have the login link handy to try their new password.
27 | Terms and condition | On click "Terms and Condition" , the URL redirect to the webpage which contains Venue delivery guide . The page should open an new tab in web browser. | SignUp Screen | Medium | 27-SignUp Terms and Condition | Available | Available | Available | Fail | Gzanfer Raqib | Shamir | GR:Terms and Conditions not found on Sign Up / Login page AA: Link directs to Voyage Control Website AZ: We have to decide what information include here
28 | Change login Email | Enter new email in the "Change Login Email" section and press the button . This will successfully send an email notification to new address. | Settings>Account | Medium | 28-Change Login Email | Available | Available | Available | Pass | Gzanfer Raqib | Shamir
29 | Decline Booking | MDS Adminc an decline the booking. After pressing the button "decline" , the status of the booking will be updated to "Declined" | List of booking>Decline | High | 29-Decline Booking by MDS Admin | Available | Available | Not Available | Pass | Gzanfer Raqib | Shamir | GR:Need to test from Admin side
30 | Email Notification for booking Declined | An email notification will be received to the vendor when the booking has been declined by MDS Admin with subject "Booking Declined" | Email | low | 30-Email notification for booking declined | Available | Available | Not Available | Pass | Gzanfer Raqib | Shamir
31 | Cancel Booking | MDS Admin and Normal Users can cancel the booking. ON click "Cancel" button on the screen, a new window will open. User provide the requireed details. This should succeesfully cancel the booking.and status should be updated as well. | List of booking>Cancel | High | 31-Cancel booking by MDS Admin | Available | Available | Not Available | Pass | Gzanfer Raqib | Shamir
32 | Email notification of booking cancelled | An email notification will be received to the vendor when the booking has been cancellled by MDS Admin with subject "Booking Cancelled" | Email | Low | 32-Email Notification for booking cancellation | Available | Available | Not Available | Pass | Gzanfer Raqib | Shamir
33 | Booking Time limit | Make a booking will not be allowed for vendor if the selected time slot is within 48 hours from the booking time. | Make a booking | High |  | Not Available | Available | Not Available | Pass | Gzanfer Raqib | Shamir
VIEWS
34 | Check all views are working | In column configuration,change the view type from the list. The list should refresh with required columns. Try all views and check all the views are working properly. | List of Booking | Low | 33-List Views | Available | Available | Not Available | Pass | Gzanfer Raqib | Shamir
REPORTS AND ANALYTICS
35 | Reports | This screen is available only for users with admin roles. Based on various filters, users can generate the Booking reports sucessfully. This report also can be downloaded in excel format and save in the system and open it without error. | Analytics | Low | 34-Reports | Not Available | Available | Available | Fail - Not tested | Gzanfer Raqib | Shamir